## Sheet1
| title | names | description | positive-evaultion | negative-evaultion | final decision
4/3/2021 | Confirm time&topics ofclient meeting | All | After the team formalization, all members reached a consensus that we need to contact our client to understand the whole project so that we can arrange our teamwork ASAP | We can grasp our client's requirements and we can distribute our workload properly based on that. We can also reserve more time to test and correct our outcome in the future. | Our client may be so busy that he cannot describe the requirement very clearly. We may not entirely understand the client's answer. | We emailed our client and made an appointment that we would meet on 9th March. Yuliang Ma, Jiawei Fan and Yuchen Wang would attend that meeting and record our client's thoughts. We will arrange our next working content based on that meeting.
9/3/2021 | Meet our client and discuss the pre-set topics | Yuliang Ma, Jiawei Fan, Yuchen Wang | We met our client and discussed with him. He showed us some demo that contains the supposed outcomes of our porject and promised that we would get our specific working content after he consult with his company members. | We made our objectives clear and adequately understanded the content of our work. We can arrange our specific workload very soon based on the strength of our team members. We can construct our project preliminarily. | We still cannot make sure what our client suppose us to do. We may find the workload is much bigger than we imagined. We meet some challenge in arranging working content because of gaps among team members. | We all agreed that our goal is to develop an inteligent algorithm that can label the user's videos automatically for the Cinefly app so that it can construct a story for each video based on its content. We may do some research in advance, meanwhile we also refer to the samples provided by our client to develop a proper algorithm. We also need to make clear deliverable schedule ASAP
10/3/2021 | Summarize feedbacks from the audit roughly | All | We experienced our first Audit and we performed our project description presentation during that. We received several useful feedback from our tutor and convenor, and we extract some critical suggestions and requirements we need to satisify. | We made our repository more professional and learned the skills that can make our presentation more clearly. | Probable it may affect our early-stage working time schedule. | We decided to enrich the content in our repository by adding more standard project managing component. We will use more images and tables in the coming tutorials and audits.
17/3/2021 | Consider to start our woking without specific data from our client | Kai, all our members | We still do not get the response from Kai. It is supposed that Kai would have offered some statistics(especially the labels of sample videos) regarding our algorithm. We have to move on | We can keep our process following the schedule. We can get more sufficient knowledge reserve before we start our work. We can arrange the working content based on our own preference and formulate the deliverable schedule more flexibly. | The final outcome may be affected because of the lack of standard statistics and reference. The product may not satisify our client's requirement entirely. | We are going to start work this weekend no matter whether we receive the response. But we will still keep communicating with our client and try to find another contact way except outlook. We will do some preliminary research to define team charters so that everyone in our team can focus on their components.
19/3/2021 | Fix our repository further | Tim, all team members | According to the suggestions from Tim, we needed to add more details to some components of our repository. It included Risk analysis in the SOW, and we also needed to present risks and time line in our landing page. Besides, we need to transform the description in our landing page to the corresponding links in our repository in github. | We can make our repository as clear and systematic as possible so that our client, tutors and convenors can observe our progress and achievements clearly. | It adds more workload to our whole team. It may also slow down the whole progress. | We decided to follow Tim's advice and worked for it.